## Sheet1
MCI Project 2020 Team #23 - Timetable
Project Title: |  | News Tone
No. | Activities |  | Week5 |  |  |  |  | Week6 |  |  |  |  | Week7 |  |  |  |  | Week8 |  |  |  |  | Week9 |  |  |  |  | Week10 |  |  |  |  | Week11 |  |  |  |  | Week12 |  |  |  |  | Week13
|  |  | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
1 | Milestone1 | Search for a Suitable Web Crawler Framework | bar: Week5 M to Week5 W
2 |  | Test the Web Crawler Framework | bar: Week5 T
3 |  | Crawl Titles of the Day on news.com.cn | bar: Week5 F
4 |  | Crawl Titles of the Day through WayBack Machine | bar: Week6 M to Week6 T
5 |  | Create a Web Crawler which can crawl Titles in past 1 month | bar: Week6 W to Week6 T
6 |  | Test the Crawler | bar: Week6 F
7 |  | B. Case & Draft Plan | bar: Week5 W to Week6 M
8 | Final Milestone | Milestone_1 Report | bar: Week7 W to Week7 F
9 |  | Extend the Crawler to Crawl Titles in past 10 years | bar: Week7 M to Week7 T
10 |  | Test the Enhanced Crawler | bar: Week7 F to Week8 T
11 |  | Unit Test - the Title Crawler | bar: Week8 W to Week9 T
12 |  | Final Milstone Plan | bar: Week8 M to Week8 F
13 |  | Testing Plan | bar: Week8 M to Week8 F
14 |  | Search for a Suitable Sentiment Analysis (SA) Framework | bar: Week7 F to Week8 T
15 |  | Test the SA Framework | bar: Week8 W to Week8 F
16 |  | Process the Raw Data (Crawled Titles) -> Input Data | bar: Week9 M to Week9 T
17 |  | Adjust the SA Framework to Fit Our Project | bar: Week9 W to Week9 T
18 |  | Test the Adjusted SA Framework | bar: Week9 F
19 |  | Apply Sentiment Analysis to the Input Data | bar: Week10 M
20 |  | Check the Analysis Results | bar: Week10 T to Week10 W
21 |  | Adjust the SA Framework -> SA Program | bar: Week10 T to Week10 F
22 |  | Analysis the Input Data with SA Program | bar: Week11 M
23 |  | Organise the Analysis Results | bar: Week11 T to Week11 W
24 |  | Unit Test - the SA Program | bar: Week11 M to Week11 F
25 |  | Create a Dashboard (Display the Analysis Results) | bar: Week10 M to Week10 F
26 |  | Display Analysis Outcomes on the Dashboard | bar: Week11 M to Week11 W
27 |  | Improve the Dashboard Performance | bar: Week11 T to Week11 F
28 |  | Unit Test - Dashboard | bar: Week11 T to Week11 F
29 |  | User Testing | bar: Week12 M to Week12 T
30 |  | Release Testing | bar: Week12 W to Week12 F
31 | Delivery | Final Report | bar: Week11 M to Week12 F
32 |  | Final Presentation Slides | bar: Week12 W to Week12 F
33 |  | Final Presentation and Demo Rehearsal | bar: Week13 M to Week13 F
Crawl all homepage titles on news.com.cn in past 10 years | bar: Week5 M
Apply sentiment analysis to the crawled titles | bar: Week5 M
Display analysis outcomes & Delivery | bar: Week5 M
Note on C22: Ying Wang: Process the Raw Data - Fitlter out meaningless characters generated during title crawling. e.g. /n/t/t - Filter out some structual words if needed
Note on C24: Ying Wang: - Randomly pick titles of 30 days - Manually check the analysis accuracy