## Jin Zhou
MCI Project Weekly Time Sheet
| Team: | #23 | Student ID: |  | a1758331 |  | Week starting: | Week 1
Week | Day | Date | Time In | Time Out | Total hours | Task | How does it fit to project plan? | Outcome/Next action
Week 1 | Monday
Tuesday
Wednesday
| Thursday | 5/3/2020 | 13:00 | 14:00 | 1 | Contact team members | Gather people together so that our team can be built | Introduce with each other and prepare for contacting superviosor
| Friday | 6/3/2020 | 12:00 | 12:30 | 0.5 | First Contact to Supervisor | Discuss the time of the meeting | Wait for the meeting
Saturday
Week 2 | Monday
Tuesday
Wednesday
| Thursday | 12/3/2020 | 15:00 | 17:00 | 2 | Do some preparation for the 1st meeting | This is the 1st group meeting and we figure out what should we ask at the meeting. | Have a brief understanding of our project
| Friday | 13/3/2020 | 11:00 | 12:00 | 1 | 1st meeting with supervisor | Figure out what is the project and how can it be completed. | Have a better understanding that what the project is, why we should do it and how we can realise it. R studio is a good tool to do the project.
| Saturday | 14/3/2020 | 13:00 | 15:00 | 2 | Search for the related information of the project | Find out what is sentiment analysis, why we need it and Look for existing application of it. | Understand what should be recorded in the pitch slides.
| Saturday | 2020-03-15 | 20:00 | 21:00 | 1 | Prepare for group meeting | Record the project progress | support member to complete week 3 meeting agenda
Week 3 | Monday | 2020-03-16 | 9:30 | 11:00 | 1.5 | Group meeting | Discuss project related problem | 1.Allocated phase tasks to team members; 2.Sepecified each member's role in this project; 3.Weekly meeting minutes recording tasks are allocated to team members.
| Tuesday | 2020-03-17 | 13:00 | 15:00 | 2 | Write the pitch draft | Identify what should we mention in the pitch presentation | The product of this project shall be used for identifying the sentiment (positive/negative) of the front page of a news web./ But why we will do that?
| Wednesday | 2020-03-18 | 11:00 | 13:00 | 2 | Continue doing research of sentiment analysis | Search for some technical example related area | We can define the progress of the project
| Thursday | 2020-03-19 | 15:30 | 5:30 | 2 | Add more content to the pitch draft | Record that how will our project be completed and summarize it in 6 steps | When we start programing, we can use the process in pitch slides as reference.
| Friday | 2020-03-20 | 9:30 | 4:30 | 1 | Review the related slides of the project | Read the meterial of pitch presentation and watch good&bad examples of presentation | Avoid the common mistakes of presentation
| Saturday | 2020-03-21 | 9:30 | 4:30 | 1 | Review the related slides of the project | Read the requirements of the following task | Prepare for the coming assgnment
| Sunday | 2020-03-22 | 14:00 | 17:00 | 3 | Technical support research | Search for some useful information of R language and R studio and send the materials to our programmer | Help team member have a better understanding of the programming language and platform
Week 4 | Monday | 2020-03-23 | 13:00 | 2:00 | 2 | Review GitHub repository structure | The project repository has been set up. | All the files that we create can be uploaded to github as evidence of what we have done.
| Tuesday | 2020-03-24 | 10:00 | 0:00 | 2 | Group meeting | Discussing project related issues | Discussed the content details of pitch presentation draft
| Wednesday | 2020-03-25 | 18:00 | 10:00 | 4 | Review pitch draft again, correct some mistakes and submit it to supervisor and my uni | Prepare for the presentation | Wait for the feedback so that we can improve our work
| Thursday | 2020-03-26 | 17:00 | 20:00 | 3 | Review all the work and submit to github | Record what we have done so far | Easier for us to make some changes of the files
| Friday | 2020-03-27
| Saturday | 2020-03-28
| Sunday | 2020-03-29
Week 5 | Monday | 2020-03-30 | 10:00AM | 12:00AM | 2 | meeting on wechat | discuss current problem and the plan for next phase | make sure the project goes correctly
| Tuesday | 2020-03-31 | 10:00AM | 2:00PM | 4 | read literatures of sentiment analysis | understand the theory of the next phases | have an idea in mid that what should do next
| Wednesday | 2020-04-01 | 10:00AM | 2:00PM | 4 | read literatures of sentiment analysis | understand the theory of the next phases | have an idea in mid that what should do next
| Thursday | 2020-04-02 | 2:00PM | 4:00PM | 2 | discuss with team members | give some bullet points of bussiness plan | it is important for a project to promote itself by a good business plan
| Friday | 2020-04-03 | 10:00AM | 2:00PM | 4 | assist to complete bussiness plan | review the previous plans as reference | understand how to write a business plan
| Saturday | 2020-04-04 | 10:00AM | 1:00PM | 3 | review business plan | review the content and correct the mistakes | improve the quality if the business plan
| Sunday | 2020-04-05 | 10:00AM | 2:00PM | 4 | read materials of tidy text | understand what is tidy text and how can It be used in the project | ensure that the crawler can be used with tidy text
Week 6 | Monday | 2020-04-06 | 10:00AM | 12:00AM | 2 | review bussiness plan again and prepard to submit | add some extra information | complete the process by teamwork
| Tuesday | 2020-04-07 | 10:00AM | 12:00AM | 2 | understand the theory of tidy text | more clearly on how to use it | lay the foundation for completing the project
| Wednesday | 2020-04-08 | 2:00PM | 6:00PM | 4 | applied tidy text to r studio to realise sentiment analysis | filter neutral words from input | obtain the words with sentiment
| Thursday | 2020-04-09 | 2:00PM | 4:00PM | 2 | record the current contribution in milesstone 1 | make everything recorded to ensure that the project is rigorous | form a good habit to record history of work
| Friday | 2020-04-10 | 2:00PM | 4:00PM | 2 | review milestone code | check the usability of codes | make sure that the contribution works well
| Saturday | 2020-04-11 | 2:00PM | 4:00PM | 2 | review draft milestone 1 report | review the content and correct the mistakes | improve the quality of the report
| Sunday | 2020-04-12
Week 7 | Monday | 2020-04-27 | 2:00PM | 4:00PM | 2 | meeting on wechat | discuss current problem and the plan for next phase | make sure the project goes correctly
| Tuesday | 2020-04-28
| Wednesday | 2020-04-29 | 2:00PM | 4:00PM | 2 | complete the first stage of sentiment analysis | display the results of sample file as figures | basiclly realise the core part of sentiment analysis
| Thursday | 2020-04-30 | 2:00PM | 6:00PM | 4 | connect crawler with algorithm | use the output of crawler as input of algorithm | verify the feasibility
| Friday | 2020-05-01 | 2:00PM | 4:00PM | 2 | review milestone reort and prepare to submit | update the report to current contribution | achieve the basic function of the project
| Saturday | 2020-05-02
| Sunday | 2020-05-03
Week 8 | Monday | 2020-05-04 | 7:00PM | 9:00PM | 2 | meeting on zoom | find out a suitable type to for the result of crawler as the input of R studio and review final milestone plan | ensure that the output of crawler can be used to R stuio and check the correctness of final milestone plan
| Tuesday | 2020-05-05 | 2:00PM | 5:00PM | 3 | test the performance of the system | use crawler output of different time range to verify the usable of system | complete the most of works of the project
| Wednesday | 2020-05-06
| Thursday | 2020-05-07 | 2:00PM | 4:00PM | 2 | discuss the limitation of the project | the ads are crawled from website | it does not affect the result too much si just ingore ads
| Friday | 2020-05-08 | 2:00PM | 6:00PM | 4 | verify the quality of system | check the accuracy by choosing 30 random days and comparing to the system | each member has different accuracies but all of them are above 85%
| Saturday | 2020-05-09
| Sunday | 2020-05-10
Week 9 | Monday | 2020-05-11 | 10:00AM | 12:00AM | 2 | meeting on wechat | discuss current problem and the plan for next phase | make sure the project goes correctly
| Tuesday | 2020-05-12
| Wednesday | 2020-05-13
| Thursday | 2020-05-14 | 2:00PM | 4:00PM | 2 | prepare to face to face and prepare the question until now | discuss the result and problem of the code | analyse the aim of the code that make sure the code is reasonable
| Friday | 2020-05-15 | 2:00PM | 6:00PM | 4 | review testing plan and final milestone plan and prepare to submit | review the content and correct the mistakes | make sure the documents follows the requirement of the project
| Saturday | 2020-05-16
| Sunday | 2020-05-17
Week 10 | Monday | 2020-05-18 | 10:00AM | 12:00AM | 2 | meeting on wechat | summarise the problems until now and plan the next phases | a progress to ensure that the project can proceed smoothly
| Tuesday | 2020-05-19
| Wednesday | 2020-05-20 | 2:00PM | 4:00PM | 2 | discuss the content of result | add the results content according to the supervisor's requiremrnts | it ensures that the project is following the correct direction
| Thursday | 2020-05-21 | 2:00PM | 4:00PM | 2 | learn to show the result in the form of webpage | supervisor's suggestion that he prefers webpage | satisfy with the requirement of custmer can help improve the quality
| Friday | 2020-05-22 | 2:00PM | 4:00PM | 2 | deal with the problem of webpage | the final aim cannot be realise if the problem hasn’t been solved | work together as a team to solve the problem
| Saturday | 2020-05-23
| Sunday | 2020-05-24 | 8:30PM | 9:30PM | 1 | discuss on a easier approach to realise out display on webpage | all good with original plan but backup plan is still required | make the project easier and safer
Week 11 | Monday | 2020-05-25 | 10:00AM | 12:00AM | 2 | meeting on wechat | review all the contributions so far | prepare for the coming task
| Tuesday | 2020-05-26 | 5:00PM | 6:00PM | 1 | first version of the project delivery done. | review the output and check if it satisfied with requirements | the project is nearly finished
| Wednesday | 2020-05-27 | 7:00PM | 8:00PM | 1 | meeting on zoom | discuss the function of webpage and poster | improve the quality of result display and make plan for next stage
| Thursday | 2020-05-28 | 2:00PM | 4:00PM | 2 | review good examples conetent of poster | have a good understand what should poster mention | make reader feel easy to understand our project
| Friday | 2020-05-29
| Saturday | 2020-05-30 | 2:00PM | 4:00PM | 2 | review good examples design of poster | have a good understand how should poster look like | make reader feel confortable to read the poster
| Sunday | 2020-05-31
Week 12 | Monday | 2020-06-01 | 10:00AM | 12:00AM | 2 | discuss the following tasks | prepare for the presentation & demo | make sure that each part can work
| Tuesday | 2020-06-02 | 2:00PM | 4:00PM | 2 | read the requirements of poster and search for a suitable tool | we decide to use Adobe Illuminate as we have somebackground knowledge of it | improve the efficiency of doing poster
| Wednesday | 2020-06-03
| Thursday | 2020-06-04 | 2:00PM | 6:00PM | 4 | learn how to use Adobe Illuminate and design the report | build the poster structure | arrange the area that which part should be placed where
| Friday | 2020-06-05 | 2:00PM | 4:00PM | 2 | coomplete the context of poster | write the overview of each phase of the project | make sure that reader can catch up the points
| Saturday | 2020-06-06 | 3:00PM | 7:00PM | 4 | use backup plans as the output webpage server is out of memory | use shiny package to load the result on a local webpage | avoid accident by backup plan
| Sunday | 2020-06-07
Week 13 | Monday | 2020-06-08 | 10:00AM | 12:00AM | 2 | practice for demo | macke sure that each member is familiar with his/her part | summarize the project with resuts
| Monday | 2020-06-08 | 2:00PM | 4:00PM | 2 | Poster review and prepare to submit | ensure that all contents are satisfied with the project plans | easier for readers to have a good understanding of the project
| Tuesday | 2020-06-09 | 2:00PM | 4:00PM | 2 | Complete abstract and introduction of final report | Describe the project overview | Summarize the object and introduce background and motivation
| Wednesday | 2020-06-10 | 1:00PM | 4:30P | 3.5 | final presentation of poster | use poster to describe the project | learn from other groups to improve presentation skills
| Thursday | 2020-06-11 | 2:00PM | 4:00PM | 2 | Approach | Describe what approaches are used in project | Describe the overall approaches
| Friday | 2020-06-12 | 2:00PM | 4:00PM | 3 | Approach | Describe techinical sections and tools | Divide the project into 2 parts, detailed introducte technical sections
| Saturday | 2020-06-13 | 2:00PM | 4:00PM | 3 | Approach | Describe the project management | Detailed introduce how management affect the project
| Sunday | 2020-06-14 | 2:00PM | 4:00PM | 2 | Result, discussion and conckusion | Describe the results and dicsuss the performance of the product | Consider the limitation and future wrok of sentiment analysis
Week 14 | Monday | 2020-06-15 | 8:00AM | 9:00AM | 1 | Review final report and submit | Summarise what has been done in the project and review each phases and the performance of the project | Have a better understanding that what the project is,what we have leant in the project so that the knowledge can be applied to real life.
| Tuesday | 2020-06-16
| Wednesday | 2020-06-17
| Thursday | 2020-06-18
| Friday | 2020-06-19
| Saturday | 2020-06-20
| Sunday | 2020-06-21
|  |  |  | Total | 148.5