## Ying Wang
MCI Project Weekly Time Sheet
| Team: | #23 | Student ID: |  | a1733805 |  | Week starting: | Week 1
Week | Day | Date | Time In | Time Out | Total hours | Task | How does it fit to project plan? | Outcome/Next action
Week 1 | Monday
Tuesday
Wednesday
| Thursday | 5/3/2020 | 13:00 | 14:00 | 1 | Contact team members | Build the team for the project | Introduce each other
| Friday | 6/3/2020 | 12:00 | 12:30 | 0.5 | First Contact to Supervisor | Asking for preparation advice for 1st meeting | Waiting for reply
Saturday
Week 2 | Monday
Tuesday
Wednesday
| Thursday | 12/3/2020 | 15:00 | 17:00 | 2 | Searching for background info. of the project | Preparing for the 1st project meeting | Knowned what the sentement analysis is, what approaches we may use to complete this project
| Friday | 13/3/2020 | 11:00 | 12:00 | 1 | Supervisor/Client meeting | Address the WHAT & WHY issues of the project | Discussed about what the project is and why we will do this project./ Further researching about these issues.
| Saturday | 14/3/2020 | 10:00 | 13:00 | 3 | Preparing for pitch | Address the WHAT & WHY issues of the project | The product of this project could be a dashborad - a program./ But what can it be used for?
| Saturday | 14/3/2020 | 20:00 | 21:00 | 1 | Preparing for group meeting | Recording the project progress | Week 3 meeting agenda
Week 3 | Monday | 16/3/2020 | 9:30 | 11:00 | 1.5 | Group meeting | Discussing project related issues | 1.Allocated phase tasks to team members; 2.Sepecified each member's role in this project; 3.Weekly meeting minutes recording tasks are allocated to team members.
| Monday | 16/3/2020 | 13:00 | 14:30 | 1.5 | Writing minutes | Recording the project progress | Minutes for week 3
| Tuesday | 17/3/2020 | 10:00 | 13:00 | 3 | Preparing for pitch | Address the WHAT & WHY issues of the project | The product of this project shall be used for identifying the sentiment (positive/negative) of the front page of a news web./ But why we will do that?
| Wednesday | 18/3/2020 | 9:30 | 4:30 | 5 | Learning R programming language | Preparing for the skills needed for this project | Getting to know R language
| Thursday | 19/3/2020 | 9:30 | 4:30 | 5 | Learning R programming language | Preparing for the skills needed for this project | Getting to know R language
| Friday | 20/3/2020 | 9:30 | 4:30 | 5 | Learning Python language | Preparing for the skills needed for this project | Getting to know Python
| Saturday | 21/3/2020 | 19:00 | 20:00 | 1 | Preparing for group meeting | Recording the project progress | Week 4 meeting agenda
Week 4 | Monday | 23/3/2020 | 10:00 | 0:00 | 2 | Create GitHub repository structure | Set up the project repository | GitHub repository
| Tuesday | 24/3/2020 | 10:00 | 0:00 | 2 | Group meeting | Discussing project related issues | Discussed the content details of pitch presentation draft
| Wednesday | 25/3/2020 | 9:30 | 2:30 | 3 | Learning Python language | Preparing for the skills needed for this project | Getting to know Python
Thursday
Friday
Saturday
Week 5 | Monday
Tuesday
Wednesday
Thursday
Friday
Saturday
|  |  |  | Total | 37.5

## Jin Zhou
MCI Project Weekly Time Sheet
| Team: | #23 | Student ID: |  | a1758331 |  | Week starting: | Week 1
Week | Day | Date | Time In | Time Out | Total hours | Task | How does it fit to project plan? | Outcome/Next action
Week 1 | Monday
Tuesday
Wednesday
| Thursday | 5/3/2020 | 13:00 | 14:00 | 1 | Contact team members | Gather people together so that our team can be built | Introduce with each other and prepare for contacting superviosor
| Friday | 6/3/2020 | 12:00 | 12:30 | 0.5 | First Contact to Supervisor | Discuss the time of the meeting | Wait for the meeting
Saturday
Week 2 | Monday
Tuesday
Wednesday
| Thursday | 12/3/2020 | 15:00 | 17:00 | 2 | Do some preparation for the 1st meeting | This is the 1st group meeting and we figure out what should we ask at the meeting. | Have a brief understanding of our project
| Friday | 13/3/2020 | 11:00 | 12:00 | 1 | 1st meeting with supervisor | Figure out what is the project and how can it be completed. | Have a better understanding that what the project is, why we should do it and how we can realise it. R studio is a good tool to do the project.
| Saturday | 14/3/2020 | 13:00 | 15:00 | 2 | Search for the related information of the project | Find out what is sentiment analysis, why we need it and Look for existing application of it. | Understand what should be recorded in the pitch slides.
| Saturday | 2020-03-14 | 20:00 | 21:00 | 1 | Prepare for group meeting | Record the project progress | support member to complete week 3 meeting agenda
Week 3 | Monday | 16/3/2020 | 9:30 | 11:00 | 1.5 | Group meeting | Discuss project related problem | 1.Allocated phase tasks to team members; 2.Sepecified each member's role in this project; 3.Weekly meeting minutes recording tasks are allocated to team members.
| Tuesday | 17/3/2020 | 13:00 | 15:00 | 2 | Write the pitch draft | Identify what should we mention in the pitch presentation | The product of this project shall be used for identifying the sentiment (positive/negative) of the front page of a news web./ But why we will do that?
| Wednesday | 18/3/2020 | 11:00 | 13:00 | 2 | Continue doing research of sentiment analysis | Search for some technical example related area | We can define the progress of the project
| Thursday | 2020-03-19 | 15:30 | 5:30 | 2 | Add more content to the pitch draft | Record that how will our project be completed and summarize it in 6 steps | When we start programing, we can use the process in pitch slides as reference.
| Friday | 2020-03-20 | 9:30 | 4:30 | 1 | Review the related slides of the project | Read the meterial of pitch presentation and watch good&bad examples of presentation | Avoid the common mistakes of presentation
| Saturday | 2020-03-21 | 9:30 | 4:30 | 1 | Review the related slides of the project | Read the requirements of the following task | Prepare for the coming assgnment
| Sunday | 2020-03-22 | 14:00 | 17:00 | 3 | Technical support research | Search for some useful information of R language and R studio and send the materials to our programmer | Help team member have a better understanding of the programming language and platform
Week 4 | Monday | 23/3/2020 | 13:00 | 2:00 | 2 | Review GitHub repository structure | The project repository has been set up. | All the files that we create can be uploaded to github as evidence of what we have done.
| Tuesday | 24/3/2020 | 10:00 | 0:00 | 2 | Group meeting | Discussing project related issues | Discussed the content details of pitch presentation draft
| Wednesday | 2020-03-25 | 18:00 | 10:00 | 4 | Review pitch draft again, correct some mistakes and submit it to supervisor and my uni | Prepare for the presentation | Wait for the feedback so that we can improve our work
| Thursday | 2020-03-26 | 17:00 | 20:00 | 3 | Review all the work and submit to github | Record what we have done so far | Easier for us to make some changes of the files
Friday
Saturday
Week 5 | Monday
Tuesday
Wednesday
Thursday
Friday
Saturday
|  |  |  | Total | 31

## Yiru Li
MCI Project Weekly Time Sheet
| Team: | #23 | Student ID: |  | a1736798 |  | Week starting: | Week 1
Week | Day | Date | Time In | Time Out | Total hours | Task | How does it fit to project plan? | Outcome/Next action
Week 1 | Monday
Tuesday
Wednesday
| Thursday | 5/3/2020 | 13:00 | 14:00 | 1 | Get in touch with team members | Build the team for the project | Have a first meeting with team members
| Friday | 6/3/2020 | 12:00 | 12:30 | 0.5 | First time contact supervisor | Get ready for the first meeting | Waiting for respond
Saturday
Week 2 | Monday | 2020-03-10 | 8:00 | 12:00 | 4 | Search materials for topic | Be prepared for the project and task | Have a good understanding of the project
Tuesday
Wednesday
Thursday
| Friday | 13/3/2020 | 11:00 | 12:00 | 1 | Supervisor/Client meeting | Address the WHAT & WHY issues of the project | Discussed the WHAT and WHY of the purpose for the project
| Saturday | 14/3/2020 | 9:00 | 13:00 | 4 | Preparing for pitch | Address the WHAT & WHY issues of the project | Discussed the project oucomes. Considered what is the best way the deliver the project to final users.
| Saturday | 14/3/2020 | 10:00 | 21:00 | 9 | Preparing for group meeting; Doing research | Recording the project progress | Week 3 meeting agenda
Week 3 | Monday | 16/3/2020 | 9:30 | 11:00 | 1.5 | Group meeting | Discussing project related issues | 1.Allocated phase tasks to team members; 2.Sepecified each member's role in this project; 3.Weekly meeting minutes recording tasks are allocated to team members.
Monday
| Tuesday | 17/3/2020 | 8:00 | 10:00 | 2 | Preparing for pitch | Address the WHAT & WHY issues of the project | The product of this project shall be used for identifying the sentiment (positive/negative) of the front page of a news web./ But why we will do that?
| Wednesday | 18/3/2020 | 8:00 | 13:00 | 5 | Learning some programming language techniques to assist me achieve my purpose. | Logic control in programming | Being familiar with programming language we are going to use
| Thursday | 19/3/2020 | 8:00 | 13:00 | 5 | Learning some programming language techniques to assist me achieve my purpose. | Object oriented progarmming | Being familiar with programming language we are going to use
| Friday | 20/3/2020 | 8:00 | 13:00 | 5 | Learning some programming language techniques to assist me achieve my purpose. | organise code in a tidy structure | Being familiar with programming language we are going to use
| Saturday | 21/3/2020 | 14:00 | 17:00 | 3 | Preparing for group meeting | Recording the project progress | Week 4 meeting agenda
Week 4 | Monday | 23/3/2020 | 8:00 | 13:00 | 5 | Study relevant algorithm | learning some knowledge about the algorithm we may apply in the project | Thinking of implementation of algorithms
| Tuesday | 24/3/2020 | 8:00 | 13:00 | 5 | Group meeting | Discussing project related issues | Discussed the content details of pitch presentation draft
| Wednesday | 25/3/2020 | 8:00 | 13:00 | 5 | Learning some programming language techniques to assist me achieve my purpose. | Preparing for the skills needed for this project | Being familiar with programming language we are going to use
Thursday
Friday
Saturday
Week 5 | Monday
Tuesday
Wednesday
Thursday
Friday
Saturday
|  |  |  | Total | 56