## Sheet1
MCI Project 2020 Team #23 - Timetable
Project Title: |  | News Tone
No. | Activities |  | Week5 |  |  |  |  | Week6 |  |  |  |  | Week7 |  |  |  |  | Week8 |  |  |  |  | Week9 |  |  |  |  | Week10 |  |  |  |  | Week11 |  |  |  |  | Week12 |  |  |  |  | Week13
 | time axis 2020-03-30 to 2020-06-12
1 | Milestone1 | Search for a Suitable Web Crawler Framework | bar: 2020-03-30 to 2020-04-01
2 |  | Test the Web Crawler Framework | bar: 2020-04-02
3 |  | Crawl Titles of the Day on news.com.cn | bar: 2020-04-03
4 |  | Crawl Titles of the Day through WayBack Machine | bar: 2020-04-06 to 2020-04-07
5 |  | Create a Web Crawler which can crawl Titles in past 1 month | bar: 2020-04-08 to 2020-04-09
6 |  | Test the Crawler | bar: 2020-04-10
7 |  | B. Case & Draft Plan | bar: 2020-04-01 to 2020-04-06
8 | Final Milestone | Milestone_1 Report | bar: 2020-04-29 to 2020-05-01
9 |  | Extend the Crawler to Crawl Titles in past 10 years | bar: 2020-04-27 to 2020-04-30
10 |  | Test the Enhanced Crawler | bar: 2020-05-01 to 2020-05-05
11 |  | Unit Test - the Title Crawler | bar: 2020-05-06 to 2020-05-12
12 |  | Final Milstone Plan | bar: 2020-05-04 to 2020-05-08
13 |  | Testing Plan | bar: 2020-05-04 to 2020-05-08
14 |  | Search for a Suitable Sentiment Analysis (SA) Framework | bar: 2020-05-01 to 2020-05-05
15 |  | Test the SA Framework | bar: 2020-05-06 to 2020-05-08
16 |  | Process the Raw Data (Crawled Titles) -> Input Data | bar: 2020-05-11 to 2020-05-12
17 |  | Adjust the SA Framework to Fit Our Project | bar: 2020-05-13 to 2020-05-14
18 |  | Test the Adjusted SA Framework | bar: 2020-05-15
19 |  | Apply Sentiment Analysis to the Input Data | bar: 2020-05-18
20 |  | Check the Analysis Results | bar: 2020-05-19 to 2020-05-20
21 |  | Adjust the SA Framework -> SA Program | bar: 2020-05-21 to 2020-05-22
22 |  | Analysis the Input Data with SA Program | bar: 2020-05-25
23 |  | Organise the Analysis Results | bar: 2020-05-26 to 2020-05-27
24 |  | Unit Test - the SA Program | bar: 2020-05-25 to 2020-05-29
25 |  | Create a Dashboard (Display the Analysis Results) | bar: 2020-05-18 to 2020-05-22
26 |  | Display Analysis Outcomes on the Dashboard | bar: 2020-05-25 to 2020-05-27
27 |  | Improve the Dashboard Performance | bar: 2020-05-28 to 2020-05-29
28 |  | Unit Test - Dashboard | bar: 2020-05-28 to 2020-05-29
29 |  | User Testing | bar: 2020-06-01 to 2020-06-02
30 |  | Release Testing | bar: 2020-06-03 to 2020-06-05
31 | Delivery | Final Report | bar: 2020-05-25 to 2020-06-05
32 |  | Final Presentation Slides | bar: 2020-06-03 to 2020-06-05
33 |  | Final Presentation and Demo Rehearsal | bar: 2020-06-08 to 2020-06-12
Crawl all homepage titles on news.com.cn in past 10 years | bar: 2020-03-30
Apply sentiment analysis to the crawled titles | bar: 2020-03-30
Display analysis outcomes & Delivery | bar: 2020-03-30
Note on C22: Ying Wang: Process the Raw Data - Fitlter out meaningless characters generated during title crawling. e.g. /n/t/t - Filter out some structual words if needed
Note on C24: Ying Wang: - Randomly pick titles of 30 days - Manually check the analysis accuracy