## Ying Wang
MCI Project Weekly Time Sheet
| Team: | #23 | Student ID: |  | a1733805 |  | Week starting: | Week 1
Week | Day | Date | Time In | Time Out | Total hours | Task | How does it fit to project plan? | Outcome/Next action
Week 1 | Monday
Tuesday
Wednesday
| Thursday | 5/3/2020 | 13:00 | 14:00 | 1 | Contact team members | Build the team for the project | Introduce each other
| Friday | 6/3/2020 | 12:00 | 12:30 | 0.5 | First Contact to Supervisor | Asking for preparation advice for 1st meeting | Waiting for reply
Saturday
Week 2 | Monday
Tuesday
Wednesday
| Thursday | 12/3/2020 | 15:00 | 17:00 | 2 | Searching for background info. of the project | Preparing for the 1st project meeting | Knowned what the sentement analysis is, what approaches we may use to complete this project
| Friday | 13/3/2020 | 11:00 | 12:00 | 1 | Supervisor/Client meeting | Address the WHAT & WHY issues of the project | Discussed about what the project is and why we will do this project./ Further researching about these issues.
| Saturday | 14/3/2020 | 10:00 | 13:00 | 3 | Preparing for pitch | Address the WHAT & WHY issues of the project | The product of this project could be a dashborad - a program./ But what can it be used for?
| Saturday | 14/3/2020 | 20:00 | 21:00 | 1 | Preparing for group meeting | Recording the project progress | Week 3 meeting agenda
Week 3 | Monday | 16/3/2020 | 9:30 | 11:00 | 1.5 | Group meeting | Discussing project related issues | 1.Allocated phase tasks to team members; 2.Sepecified each member's role in this project; 3.Weekly meeting minutes recording tasks are allocated to team members.
| Monday | 16/3/2020 | 13:00 | 14:30 | 1.5 | Writing minutes | Recording the project progress | Minutes for week 3
| Tuesday | 17/3/2020 | 10:00 | 13:00 | 3 | Preparing for pitch | Address the WHAT & WHY issues of the project | The product of this project shall be used for identifying the sentiment (positive/negative) of the front page of a news web./ But why we will do that?
| Wednesday | 18/3/2020 | 9:30 | 4:30 | 5 | Learning R programming language | Preparing development skills for the project | Getting to know R language
| Thursday | 19/3/2020 | 9:30 | 4:30 | 5 | Learning R programming language | Preparing development skills for the project | Getting to know R language
| Friday | 20/3/2020 | 9:30 | 4:30 | 5 | Learning Python language | Preparing development skills for the project | Getting to know Python
| Saturday | 21/3/2020 | 19:00 | 20:00 | 1 | Preparing for group meeting | Recording the project progress | Week 4 meeting agenda
Week 4 | Monday | 23/3/2020 | 10:00 | 0:00 | 2 | Create GitHub repository structure | Set up the project repository | GitHub repository
| Tuesday | 24/3/2020 | 10:00 | 0:00 | 2 | Group meeting: discussed details of pitch presentation draft | Discussing project related issues | Minutes week 4
| Wednesday | 25/3/2020 | 9:30 | 4:30 | 5.5 | Learning Java | Milestone1 in progressing | Learned how to programming with Java
| Thursday | 26/3/2020 | 13:00 | 17:00 | 3.5 | Learning Servlet | Milestone1 in progressing | Learned Java servlet principle
| Friday | 27/3/2020 | 10:00 | 17:00 | 5 | Learning Servlet | Milestone1 in progressing | Learned Java servlet principle
| Friday | 27/3/2020 | 19:00 | 21:00 | 2 | Group meeting: Discussing the details of pitch video recording, testing the tools for video recording | Pitch presentation | Each member will record its own part as allocated, and then Jin Zhou will assemble all videos together
| Friday | 27/3/2020 | 20:30 | 22:00 | 1.5 | Preparing for the pitch presentation draft | Pitch presentation | write down speech draft of my part
| Saturday | 28/3/2020 | 10:00 | 0:00 | 2 | Presentation rehearsal | Pitch presentation | practiced speech and a demo is recorded
| Sunday | 29/3/2020 | 9:30 | 11:00 | 1.5 | Recording pitch video | Pitch presentation | my part is recorded as a video and is sent to Jin Zhou
Week 5 | Monday | 2020-03-31 | 10:00 | 13:00 | 3 | Learning Scrapy | Milestone1 in progressing | Learned how to access a web page with scrapy, and some basic operations provied by scrapy
| Monday | 2020-03-31 | 14:00 | 16:00 | 2 | Group meeting: Discussed the details of business case and milstone1 draft plan, roles responsibility and tasks. | Assignment-B.Case & Draft Plan | Minutes for week 5
| Tuesday | 2020-03-31 | 13:30 | 17:30 | 4 | Learning Java | Milestone1 in progressing | Learned how to programming with Java
| Wednesday | 2020-04-01 | 9:00 | 11:00 | 2 | Learning Servlet | Milestone1 in progressing | Learned Java servlet principle
| Wednesday | 2020-04-01 | 13:30 | 18:00 | 4 | Learning Servlet | Milestone1 in progressing | Learned Java servlet principle
| Thursday | 2020-04-02 | 9:30 | 5:30 | 6 | Learning R programming language | Preparing development skills for the project | Getting to know R language
| Friday | 2020-04-03 | 9:30 | 4:30 | 4 | Learning R programming language | Preparing development skills for the project | Getting to know R language
| Friday | 2020-04-03 | 20:00 | 21:00 | 1 | Group chating | Assignment-B.Case & Draft Plan | Talking about some confusing issues about B.Case and draft plan.And plan to contact the supervisor (Nick) for help.
| Saturday | 2020-04-04 | 9:30 | 11:30 | 2 | Lecture - Risk Management | Learn to manage the risk of our project | Watched the recording, filed the notes
| Sunday | 2020-04-05 | 9:30 | 12:30 | 3 | Create draft plan for milstone 1 | Milestone1 draft plan | Milestone1 plan v1.0
| Sunday | 2020-04-05 | 19:00 | 21:00 | 2 | Improve milestone 1 draft plan | Milestone1 draft plan | Milestone1 plan v1.1
Week 6 | Monday | 2020-04-06 | 10:00 | 12:00 | 2 | Group meeting: dicussed issues about B.case & Draft Plan | Assignment-B.Case & Draft Plan | Minutes for week 6
| Monday | 2020-04-06 | 15:00 | 18:00 | 3 | Improve milestone 1 draft plan | Assignment-B.Case & Draft Plan | B.Case & Draft Plan v1.1
| Tuesday | 2020-04-07 | 10:00 | 17:00 | 5 | Scrapy: crawl news titles from news.com.au | Milestone1 in progressing | Crawled info. as tutorial shows
| Wednesday | 2020-04-08 | 10:00 | 16:00 | 4 | Study the HTML file structure with Google Chrome developer tools | Milestone1 in progressing | knowned what is tag and its properties
| Thursday | 2020-04-09 | 9:30 | 16:00 | 5 | Study the HTML file structure with Google Chrome developer tools | Milestone1 in progressing | can access expected tags and its properties with Scrapy
| Friday | 2020-04-10 | 9:30 | 18:30 | 7 | Scrapy: crawl news titles from news.com.au | Milestone1 in progressing | can crawl date and all titles of one page
| Saturday | 2020-04-11 |  |  | -
| Sunday | 2020-04-12 |  |  | -
Break 1 | Monday | 2020-04-13 |  |  | -
| Tuesday | 2020-04-14 |  |  | -
| Wednesday | 2020-04-15 |  |  | -
| Thursday | 2020-04-16 | 9:30 | 13:00 | 3 | Scrapy: crawl news titles from news.com.au | Milestone1 in progressing | Checked the crawled titles and make sure all crawled info. are as expected
| Friday | 2020-04-17 | 9:30 | 13:00 | 3 | Unit test: make sure the basic crawler operate stably | Milestone1 in progressing | Unit test passed
| Saturday | 2020-04-18 |  |  | -
| Sunday | 2020-04-19 |  |  | -
Break 2 | Monday | 2020-04-20 |  |  | -
| Tuesday | 2020-04-21 | 13:00 | 16:30 | 3 | Designing the program achitecture | Milestone1 in progressing | Crawled one page of news.com.au via Wayback Machine.
| Wednesday | 2020-04-22 | 11:00 | 20:00 | 6 | Designing the program achitecture | Milestone1 in progressing | Tried to figure out how to automatically crawl all pages next.Tried many methods but failed.
| Thursday | 2020-04-23 | 10:45 | 20:30 | 6 | Designing the program achitecture | Milestone1 in progressing | Thinking about how to analyse content. Figure out some methods
| Friday | 2020-04-24 | 9:30 | 17:00 | 5 | Designing the program achitecture | Milestone1 in progressing | Thinking about the final shape of our project. Software or web app?
| Saturday | 2020-04-25 |  |  | -
| Sunday | 2020-04-26 |  |  | -
Week 7 | Monday | 2020-04-27 | 10:00 | 23:00 | 1 | Group meeting: discussed issues about searching for suitable sentiment analysis framework | Milestone1 in progressing | Minutes for week 7
| Tuesday | 2020-04-28 | 9:30 | 11:30 | 2 | Lecture - Testing | Testing plan preparation | Watched the recording, filed the notes
| Wednesday | 2020-04-29 | 10:00 | 17:00 | 6 | Reformatting JSON files | Apporprite format will ease the R analysing progress | JSON files is successfully imported into the R. The next step is to analysis the data.
| Thursday | 2020-04-30 | 11:00 | 17:00 | 5 | Applying right manipulation to the data | It could produce accurate analysis result | tidytext would be the best to be applied to improve the project
| Friday | 2020-05-01 | 10:00 | 15:00 | 4 | Study the feasiblity of tidytext | tidytext is a powerful tool of analyse sentiment in the text | Study the thesis of tidytext to help me understand how the tidy text works
| Saturday | 2020-05-02 | 11:00 | 15:00 | 4 | Study the feasiblity of tidytext | tidytext is a powerful tool of analyse sentiment in the text | Study the thesis of tidytext to help me understand how the tidy text works
| Sunday | 2020-05-03 |  |  | -
Week 8 | Monday | 2020-05-04 | 10:00 | 12:00 | 2 | Group meeting: discussed about how to analyse the crawled titles | Final milestone in progressing | Minutes for week 8
| Tuesday | 2020-05-05 | 11:00 | 18:00 | 6 | Final Milestone Plan | Assignment-Final Milestone Plan | Final Milestone Plan v1.0
| Wednesday | 2020-05-06 | 10:00 | 11:00 | 1 | Imprved Final Milestone Plan | Assignment-Final Milestone Plan | Final Milestone Plan v1.1
| Thursday | 2020-05-07 | 9:30 | 11:30 | 2 | Convert JSON file to XLSX file | Final Milestone in progressing | As the R language cannot deal with the JSON file, we need to convert it to proper file format - XLSX.Tried many methods but failed.
| Friday | 2020-05-08 | 10:00 | 14:00 | 3 | Convert JSON file to XLSX file | Final Milestone in progressing | Converted JSON to XLSX with python (panda package).Next do the sentiment analyse with Rstudio.
| Saturday | 2020-05-09
| Sunday | 2020-05-10
Week 9 | Monday | 2020-05-11 | 10:00 | 12:00 | 2 | Group meeting: discussed issues about testing plan, and how to display sentiment analysis outputs | Assignment-Testing Plan | Minutes for week 9
| Monday | 2020-05-11 | 14:00 | 15:00 | 1 | Client meeting: discussed issues about the final shape of our products. | Final Milestone in progressing | Nick prefers a webpage to show the sentiment analysis results.Other requirements recorded.
| Tuesday | 2020-05-12 | 10:00 | 18:00 | 5 | Searching for suitable analysis framework in R | Final Milestone in progressing | Tried many methods but failed.
| Wednesday | 2020-05-13 | 9:30 | 15:00 | 4 | Searching for suitable analysis framework in R | Final Milestone in progressing | Suitable anslysis frameword found - tidy_text in R
| Thursday | 2020-05-14 | 10:00 | 20:00 | 6 | tidy_text in R: sentiment analysis | Final Milestone in progressing | Generated barcharts that shows the distribution of the general tone of one year news titles
| Friday | 2020-05-15 | 9:30 | 14:00 | 3 | tidy_text in R: sentiment analysis | Final Milestone in progressing | Generated general tone for all 10 years
| Saturday | 2020-05-16 |  |  | -
| Sunday | 2020-05-17 |  |  | -
Week 10 | Monday | 2020-05-18 | 10:00 | 12:00 | 2 | Group meeting: Discussed about the tools for building webpage to display sentiment analysis outputs | Final milestone in progressing | Minutes for week 10
| Tuesday | 2020-05-19 | 9:30 | 14:00 | 3 | Check the analysis results | Final Milestone in progressing | It seems that some words have unreasonably high appearance frequency. Fix the bugs next.
| Wednesday | 2020-05-20 | 9:30 | 20:00 | 8 | Combine Java servlet web server with the R | Java servlet web server could works as the back-end program which provide neceaasry service for the users of our program | Creating the base architecture of the Java Servlet program
| Thursday | 2020-05-21 | 13:00 | 18:00 | 5 | Combine Java servlet web server with the R | Java servlet web server could works as the back-end program which provide neceaasry service for the users of our program | Testing the clients request monitoring, and server reponse to clients.
| Friday | 2020-05-22 | 13:00 | 17:00 | 4 | Combine Java servlet web server with the R | Java servlet web server could works as the back-end program which provide neceaasry service for the users of our program | Writing logic control for the service
| Saturday | 2020-05-23 | 11:00 | 17:00 | 5 | Combine Java servlet web server with the R | Java servlet web server could works as the back-end program which provide neceaasry service for the users of our program | Combining the Java Servlet with the R
| Sunday | 2020-05-24 |  |  | -
Week 11 | Monday | 2020-05-25 | 10:00 | 12:00 | 2 | Group meeting: discussed issues related to final demonstration | Final Demo & Presenttation | Minutes for week 11
| Tuesday | 2020-05-26 | 9:30 | 19:00 | 8 | Java servlet deployment | Finishing the program integration | Using external packages to coordinate Java and the R
| Wednesday | 2020-05-27 | 10:30 | 14:00 | 3 | Java servlet deployment | Finishing the program integration | Using external packages to coordinate Java and the R
| Wednesday | 2020-05-27 | 11:00 | 16:00 | 4 | Tomcat servlet container setup | Finishing the program integration | configuring the tomcat java servlet conntainer
| Thursday | 2020-05-28 | 10:00 | 16:00 | 5 | Tomcat servlet container setup | Finishing the program integration | configuring the tomcat java servlet conntainer
| Friday | 2020-05-29 | 10:00 | 12:00 | 2 | Tomcat servlet container setup | Finishing the program integration | Testing the tomcat Javaservlet container
| Saturday | 2020-05-30 | 14:00 | 20:00 | 6 | Testing the Shiny and Java servlet | Comparing the performance between shiny and Java servlet | shiny is used for demo, and Java Servlet is used for final clients
| Sunday | 2020-05-31 |  |  | -
Week 12 | Monday | 2020-06-01 | 10:00 | 12:00 | 2 | Group meeting: discussed issues related to poster production | Final Demo & Presenttation | Minutes for week 12
| Tuesday | 2020-06-02 | 10:00 | 11:00 | 1 | Improving program website | Poster | Flow chart of crawler processing logic
| Wednesday | 2020-06-03 | 13:00 | 17:00 | 4 | Write final report | Final report | MCI_final_report_v1.0
| Thursday | 2020-06-04 | 13:00 | 16:00 | 3 | Finishing final demo poster | Final demo poster in grogress | Discuss the outcome of final demo poster with other group members, and trying to improve it.
| Friday | 2020-06-05 | 10:00 | 12:00 | 2 | Finishing final demo poster | Final demo poster in grogress | Using Aadobe illustrator to redesign the poster
| Saturday | 2020-06-06 | 13:00 | 15:00 | 2 | Improve the final report | Final report | MCI_final_report_v1.1
| Sunday | 2020-06-07 | 10:00 | 11:00 | 1 | Improve the final report | Final report | MCI_final_report_v1.2
Week 13 | Monday | 2020-06-08 | 10:00 | 12:00 | 2 | Group meeting: discussed issues related to poster production | Final Demo & Presenttation | Rehearsaled presentation & Demo; Minutes for week 13
| Monday | 2020-06-08 | 14:00 | 17:30 | 3 | Improve the final report; Demo Rehearsal | Final report + Final Demo & Presenttation | MCI_final_report_v1.3, Demo Rehearsal
| Tuesday | 2020-06-09 | 14:00 | 17:00 | 3 | Improve the final report; Demo Rehearsal | Final report + Final Demo & Presenttation | MCI_final_report_v1.4, Demo Rehearsal
| Wednesday | 2020-06-10 | 14:30 | 16:30 | 2 | Preparing final presentation | Final Demo & Presenttation | Completed the Final Demo & Presenttation
| Friday | 2020-06-12 | 15:00 | 16:30 | 1.5 | Arrange project management doc | Project Management | Sorted out the docs
| Saturday | 2020-06-13 |  |  | -
| Sunday | 2020-06-14 |  |  | -
|  |  |  | Total | 281